## Emprendepyme shop
VISITA emprendepymeshop
Ver Plantilla Premium
Ver Plantilla Premium

## Plan de operaciones
Plan Operaciones Anual
Actividad | Responsable | Data transfer | Herramienta / Formulario | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar
Identify groups and farmers; inform about ICS | Extension officer |  | Meetings and group discussions, preliminary assessment
Risk assessment | Head of extension |  | Risk assessment checklist
Application of individual members to primary cooperative | Primary Coop |  | Farmer’s application with signature
Contracting farmers | ICS manager | Enter contracted farmers into data base; transfer list of registered farmers to technicians and facilitators | Farmer agreement, internal regulations
Training of ICS technicians | ICS manager | Enter conducted trainings and participants into data base. | Training reference materials
Training farmers on ICS and organic production | Extension officer |  | Farmer diary, ICS formats, list of participants
Document profile data of farms, draw maps | Facilitator | Enter number of productive trees and estimated production into data base | Farmer diary, base line information questionnaire, farmer register
Internal inspection of nursery | Internal inspector | Enter number of nurseries and estimated number of seedling production and distribution. | Inspection report nursery
Monitoring and technical advice visit to farms | Facilitator | Enter visits in farmer diary | Farmer diary, farmer register (enter visits)
Internal inspection of farm | Internal inspector | enter inspection dates and harvest estimates into data base; prepare farmers list for approval | Inspection report farm
Internal inspection of pulping centre | Internal inspector | enter results of inspections into data base | Inspection report pulping centre
Supervise internal inspection activities | ICS manager | enter re-inspected farms into database | Register of re-inspected farms / pulping centres / nurseries
Approval decisions for farms, pulping centres and nurseries | Approval committee / ICS manager | enter approval decisions into data base; transfer approved farmers list and harvest estimates to pulping centres | Inspection report, approved list of farmers
Fresh cherry delivery to pulping centre | Pulper operator | enter volumes of fresh cherry collected (per farmer) in data base. Prepare total fresh cherry delivered by farmer, total fresh cherry pulped and total dry parchment produced from each group. | Register of fresh cherry delivery with harvest estimate
Delivery of parchment to processing centre | Marketing manager | enter into data base | Register of dry parchment delivery
Hulling of dry parchment, grading/sorting | Marketing manager | enter into data base. | Register of hulling activities
External inspection | Certification body / ICS manager |  | List of approved farms / pulping centres / nurseries
Selling of green beans | Marketing manager | enter into data base | Register of sales